Engagement and Monitoring of Assistants to Teachers of Serbian as a Non-Mother Tongue in Selected Elementary Schools in Bujanovac and Preševo

FIRST PROGRESS REPORT

(End of September 2018 to November 2018)

Ref. UNOPS- EUPRO-2018-S-006

November, 2018

Introduction

The First Progress Report has been specified as a deliverable in the Contract for Services UNOPS- EUPRO-2018-S-006, related to the consulting services in respect of engagement and monitoring of assistants to teachers of Serbian as a non-mother tongue in 4 elementary schools in Bujanovac and Preševo. The Progress Report was prepared by Robert Kozma, the Project Coordinator, on 26 November 2018.

#### Background

One of the characteristics of Bujanovac and Preševo as post-conflict municipalities is the protracted polarisation of citizens based on their ethnicity and language. This polarisation is also visible in the education system. Schools are not based on ethnic background of students. However, there are separate schools in which teaching is either in Serbian or Albanian. School students of mainly Albanian ethnicity attend schools with tuition in the Albanian language and vice versa, school students of Serbian ethnicity attend schools with tuition in the Serbian language. Children of Roma ethnicity mainly attend the latter schools. Students in the schools where teaching is in Albanian have obligatory subject of Serbian as a non-mother tongue, while there are no courses of the Albanian language as the language of local community offered in schools with teaching in the Serbian language. Inadequate knowledge of the Serbian language among youth of the Albanian national minority seriously damages their opportunities for further education and employment in Serbia, while the lack of bilingualism among all citizens hampers social cohesion in these municipalities. In 2014, the Coordination Body for Preševo, Bujanovac and Medveđa (CBO) conducted research and the following report: the “Study on the Possibilities for Improvement of Teaching/Learning of Serbian as a Non-Mother Tongue in Preševo, Bujanovac and Medveđa”. They have detected that only 5% of Albanian school children from 16 elementary schools encompassed by research have functional ability to communicate in Serbian. One of the main reasons for shortcomings in teaching Serbian as a non-mother tongue is the lack of qualified staff. Because of that, authors of the Study proposed introduction of teaching assistants with appropriate qualifications in teaching methodology of Serbian as a non-mother tongue.  Since 2015, a confluence of stakeholders have supported and implemented recommendations specified in the Study, enabling for six teaching assistants to be engaged in four elementary schools in Preševo and Bujanovac. Project “Engagement and Monitoring of Assistants to Teachers of Serbian as a Non-Mother Tongue in Selected Elementary Schools in Bujanovac and Preševo” builds on the results of previous actions and aims to contribute to the recommendation of the Study and to improvement of social cohesion of Bujanovac and Preševo.

Milestone I – 25 September to 22 November 2018

- Communication and coordination of the key project stakeholders

- The TAs engaged regularly in delivery of classes of Serbian as a Non-Mother Tongue

- Executed regular supervision, management and monitoring of the TAs work;

- Regular communication with the schools, ensuring project implementation in accordance with the work plan;

- TAs participated in training courses for teachers of Serbian as a non-mother tongue;

- Prepared and delivered the baseline testing of school students

Output 1: Communication and coordination of the key project stakeholders (Ministry of Education, Coordination Body for Preševo, Bujanovac and Medveđa, EU PRO)

Activity 1.1: Held one meeting with the representatives of CBO and EU PRO

The Project Team representatives, together with the representatives of CBO and EU PRO organised a meeting on 11 October 2018. The topic of the meeting was the organisation of the baseline testing and other related project issues.

Activity 1.2: Regular communication and coordination

Regular communication among all key stakeholders maintained in this reporting period. On 6 November 2018 the formal letter was sent to the Ministry of Education, Science and Technological Development regarding testing of school students in the selected elementary schools in Bujanovac and Preševo. After the approval of the Ministry of Education, the Coordination Body for Preševo, Bujanovac and Medveđa (CBO) immediately informed respective schools about the testing. CBO also informed and invited School Administration of MESTD – Leskovac to the forthcoming testing of school students.

Output 2: The TAs engaged regularly in delivering classes of Serbian as a Non-Mother Tongue

Activity 2.1: The TAs regularly assist in delivering classes

Assistants to teachers are teaching Serbian as a non-mother tongue in 36 classes of 3rd, 4th, 5th, 6th and 8th grades and one combined class (3rd and 4th grade), together with nine teachers of the Serbian language. The overall number of school students covered with the project is 738. There are 398 male students and 340 female students.

The assistants to teachers have an obligation to send monthly reports referring to their work with school students, applied teaching methods, curriculum and class units, as well as relation with students and teachers. Below is a review of TAs work in period from September to November 2018:

- TAs Impression of the executed work with school students and achievement of students

The assistants to teachers deployed in two schools in the Preševo municipality are very well accepted by school students and have quite good cooperation with delegated teachers of the Serbian language, while the assistants deployed in two schools in the Bujanovac municipality have reported a low level of students’ knowledge of Serbian, so the communication with them is difficult. One assistant emphasised the importance of renewing the previously learnt lessons prior to learning the new ones.

Assistants reported that school students are interested in learning Serbian, but there is a strong need for renewal of lessons and acquired knowledge from the previous school year. It is necessary to simplify the learning material extensively in order for school students to acquire the basic communication knowledge in the Serbian language. Assistants will also organise additional lessons of the Serbian language, emphasise group work and work in pairs, the use of audio and video content, etc.

- Cooperation with teachers

Five of six assistants reported good cooperation with delegated teachers, while assistant Ms Marija Kostadinović had a problem in cooperation with the delegated teacher, Ms Tevide Ramadani at the very beginning.

The assistants to teachers underlined the following issues that occurred occasionally in cooperation with teachers:

- the lack of cooperation between teacher and assistant during execution of classes

- assistants sometimes work alone with school students, without teacher being present at the class

- no joint preparation of lessons with delegated teachers

- Work-related difficulties

The newly-assigned assistant, Ms Marija Kostadinović, reported a problem at the beginning of her engagement with the delegated third grade teacher, who was reluctant to accept any assistants. Upon consultations with the school principal, it was decided that Marija will work with one class of 6th grade instead of the originally planned 3rd grade.

During October two assistants to teachers reported serious problems in cooperation with teachers:

- The delegated teacher, Ms Tevide Ramadani, from “Ibrahim Keljmendi” Elementary School in Preševo complained on the work of the newly-assigned assistant, Ms Marija Kostadinović. The Project Team immediately organised a meeting in Preševo with the school principal and separated meetings with the delegated teacher and the assistant, on 16 October 2018. The Project Team emphasised the importance of close cooperation and both sides accepted the recommendations and the dispute was resolved.

- The newly-assigned assistant to teacher, Mr Vlada Petrović reported about the problem with the delegated teacher, Mr Naim Sadiu. The teacher was often absent from classes, while during such classes school students provoked the assistant referring to nationality and political issues, both in the classroom and in the school hallway. In conversation between the assistant and Group the 484 representative, it was agreed that the assistant should first talk with the teacher and then, if situation stayed unresolved, the Group 484 representative would talk with the school principal. At the meeting, the assistant explained the teacher the importance of him being present at classes and their close cooperation. The discussion was productive, resolved the situation, leading to cooperation during classes; the teacher is now rarely absent from classes.

- Consultations / meetings/ cooperation between assistants

Assistants closely cooperate with their colleagues deployed in the same town, while cooperation with assistants deployed in other town is quite rare. All assistants previously engaged in the program offered necessary support to two newly assigned assistants. Communication among the assistants was related to programs and experience sharing, as well as exchange of literature and previously produced learning materials.

Activity 2.2: Extracurricular activities

Twice a week, four assistants (Ms Brankica Živković, Mr Vlada Petrović, Mr Marko Radulović and Ms Ivana Milenković) attend the free course of the Albanian language organised in Bujanovac by the OSCE – Mission in Serbia. The assistant deployed in Preševo reported that students of 6th grade expressed their wish to have additional classes of the Serbian language, so it was agreed with the teacher to organise additional classes once a week, prior to the first class with these students.

Ms Brankica Živković reported that Mr Zoran Stanković, the president of the Coordination Body for Preševo, Bujanovac and Medveđa of the Government of the Republic of Serbia visited “Naim Fraseri” Elementary School in Bujanovac on 20 September 2018. He attended the class of the Serbian language as a non-mother tongue and communicated with school students in Serbian. The students prepared a performance with recitations for that occasion.

Media references:

http://rtv.rs/sr_lat/drustvo/zoran-stankovic-obisao-opstinu-bujanovac_951712.html

http://www.kt.gov.rs/sr/news/arhiva-vesti/stankovic-vise-od-600-albanskih-djaka-uci-srpski-jezik-kao-nematernji/

https://www.youtube.com/watch?v=qZKtmNTTh3s *** from 13:10 - part that refers to the visit***

http://www.rts.rs/page/tv/sr/story/21/rts-2/3268713/gradjanin.html  ***from 15:10 - part that refers to the visit***

Output 3: Executed regular supervision, management and monitoring of the TAs work

Activity 3.1: Meeting with the representatives of “Ibrahim Keljmendi” Elementary School

During previous month and the half of the project implementation, we only had one serious problem in cooperation between teachers and assistants to teachers, which needed interference of the school principal and the Project Team. It was the problem related to cooperation between the assistant, Ms Marija Kostadinović and the teacher Ms Tevide Ramadani in “Ibrahim Keljmendi” Elementary School in Preševo. The Project Team members, Mr Robert Kozma and Ms Katarina Najdanović visited the school on 16 October 2018. First, it was agreed with the school principal that we should stress the need for mutual cooperation between the teacher and the assistant and send a strong message that it is unacceptable that the teacher insists to have another person for an assistant, she had realised good cooperation in the previous year, or to insist that the assistant should be engaged in other grades. Separate meetings were organised with the teacher Ms Tevide Ramadani and the assistant Ms Marija Kostadinović. Both meetings were held in the office of the school principal.  During the meetings it was concluded that there was no cooperation between the delegated teacher and the assistant. We all agreed that it was necessary to have mutual communication between the two of them. They both agreed to have separate meetings and agree and talk about the structure of classes, their particular obligations in preparation and execution of classes. The Project Team emphasised the importance of close cooperation and both sides accepted the recommendation, resolving the problem in an amicable manner.

Activity 3.2 Maintain regular communication with the assistants and review of regular TAs monthly reports

Besides teaching, the assistants have an obligation of preparing and submitting monthly reports, where they will summarise their activities. The deadline for the submission of September monthly reports was 23 September 2018. All further reports need to be submitted to Group 484 on the twentieth of the month. September reports were very well prepared by four assistants, who had been previously engaged as assistants, while two newly selected assistants to teachers provided us with brief reports. Group 484 provided these two assistants with comments/suggestions on how to improve their reports, what they eventually did. October reports were properly prepared by all the deployed assistants. The communication with the assistants was regular. They informed Group 484 about any deviation in the work (absence of teachers during the class, day off, school day, etc.) Group 484 informed the assistants about the planned testing, potential training courses, etc. In addition, Group 484 paid special attention to the issues from the field, such as the problem in “Ibrahim Keljmendi” Elementary School. After the organised meeting in Preševo, we were in constant contact with the engaged assistant, Ms Marija Kostadinovic in order to see progress in the cooperation between the delegated teacher and the assistant.

The Project team maintained regular communications and field visits with the assistants. Following meetings were organized during the reporting period:

- 29 October 2018 - Meeting with the four assistants during the international scientific conference. Ms Katarina Najdanović, the Project Team member, met with the four assistants during the conference and they discussed the work-related topics (teaching methods, cooperation with students and teachers, as well as potential problems).

- 14/15 November 2018 - During testing of students of 3rd and 5th grades, we used the opportunity to meet all the engaged assistants and discuss the work-related topics. Besides the usual problems (presence of teachers during execution of classes, preparation of the learning material, absence of school dairies, etc.) the assistants emphasised the importance of continuation of this project

Output 4: Regular communication with the schools, ensuring project implementation in accordance with the work plan

Activity 4.1. Maintain regular communication with all the schools and the field visits

Project team maintained regular communication with teacher assistants during previous period, while communication with school principals and appointed teachers were sporadic, although regular, and when needed. Most of the communication with school principals was related to the organisation of the baseline testing, which was scheduled for 14 and 15 November 2018.

During the reporting period several meetings were organised with school principals and the assistants on the field:

- 16 October 2018 - Meeting with the school principal, the teacher and the assistant in the “Ibrahim Keljmendi” Elementary School. Please see details in the section Activity 3.1.

- 14/15 November 2018 - During testing of students of 3rd and 5th grades, we also met the school principals in Veliki Trnovac, Bujanovac and Oraovica and they emphasised the importance of having assistants in teaching Serbian as a Non-mother tongue and they were very interested in the testing results.

Output 5: Professional development of TAs through their participation in expert seminars

Activity 5.1: Participation of TAs in training for implementation of new curriculum for the subject of Serbian as a non-mother tongue

All the engaged teaching assistants participated in training on learning outcomes of the new curricula for Serbian as a non-mother tongue for the first and the second cycle of education, in Bujanovac and Preševo, which was organised by the MESTD, the Institute for the Advancement of Education and OSCE – Mission in Serbia.

The training for teachers held on 22 September 2018 in Preševo and Bujanovac was about the implementation of the new curriculum for the subject of Serbian as a non-mother tongue for the first and second cycle of compulsory education. The topic of the training was the implementation of the new curriculum for the first and fifth grades of elementary education. The training was carried out by experts from the Centre for Serbian as a Foreign Language from Belgrade and Novi Sad (Ms Nataša Dobrić, Ms Jelena Redli, Mr Aleksandar Dognar, and Ms Nikica Strižak). The assistants expressed satisfaction with the organised training and possible implementation of the acquired knowledge in the realisation of teaching in the future. During the training it was pointed out that the aim of teaching Serbian as a non-mother tongue was to train students for basic communication in the Serbian language, and accordingly teachers were recommended the use of A program (learning the Serbian language in homogeneous areas i.e. in which national minority is majority in relation to overall local population), and it was emphasised that all the simplifications and adaptations of materials were welcomed in order to achieve the goal. The assistants believe that the practical part of the training was very useful. Acquired knowledge can be used in everyday work with children (access to students, way of realisation of the teaching units, examples of exercises, etc.).

Activity 5.2: Participation of TAs in international scientific conference “Serbian as the Foreign Language in Theory and Practice”

The Faculty of Philology (the University of Belgrade), OSCE – Mission in Serbia and the Centre for Serbian as a Foreign Language organised an international scientific conference “Serbian as the Foreign Language in Theory and Practice” at the Faculty of Philology in Belgrade, on 26-28 October. The four engaged assistants were present there in order to learn new methods and innovative tools for teaching Serbian as a non-mother tongue. Ms Brankica Živković had a presentation of her work, titled “The Drama Method in Teaching Serbian as a Non-Mother Tongue”.

Output 6: Prepared and delivered baseline testing of the school students

Activity 6.1:  Scheduling of baseline testing

Preparatory activities for baseline testing started in October 2018. At the meeting of the Project Team representatives on 11 October 2018, experts for Serbian as a foreign language and the EU PRO representative agreed for the baseline testing to be held on 14 -15 November 2018. The Project Team decided to organise the baseline testing in November, which had originally been planned for October, because the experts for Serbian as a foreign language were available to prepare the tests only during November. The baseline testing did not cover the students of 4th and 6th grades because they had been tested in late May and then in October 2018, in the organisation of OSCE.

On 6 November 2018, the formal letter was sent to the Ministry of Education, Science and Technological Development regarding testing of school students in the selected elementary schools in Bujanovac and Preševo. After the approval of the Ministry of Education, the Coordination Body for Preševo, Bujanovac and Medveđa (CBO) immediately informed respective schools about the testing. CBO also informed and invited School Administration of MESTD – Leskovac to the forthcoming testing of pupils. Representative of School Administration of MESTD – Leskovac was present during the testing in Bujanovac.

Activity 6.2: Preparatory activities with the schools

The school management was informed about baseline testing through the formal letter sent by the Coordination Body for Bujanovac, Preševo and Medveđa on 6 November 2018. School principals offered full support in the organisation of testing. Since it was not possible to have testing during classes of the Serbian language, the school principals organised testing during other classes. All the teachers of the Serbian languages offered support in testing, but experts for Serbian as a foreign language thought that it was better for school students if assistants and teachers were absent during testing.

Activity 6.3: Realisation of baseline testing

On 14 November, baseline testing was organised in Veliki Trnovac/Bujanovac in “Muharem Kadriu” Elementary School (classes: V1, V2, III1 and III2) and “Naim Frašeri” Elementary School (classes: III1 and III2), while it was organised in “Selami Halači” Elementary School (classes: V1 and V2), in Oraovica, Preševo, on 15 November. The students of 3rd and 5th grades were tested, 163 students in total. The baseline testing did not cover the students of 4th and 6th grades (530 students in total) because they were tested in late May and in October 2018. This test will serve as baseline for measuring further improvement of school students’ knowledge of the Serbian language throughout the project implementation. Experts for Serbian as a foreign language are currently assessing students’ achievements at the test.

Risks and issues:

Possible risks in the implementation of action are related to communication and cooperation with schools and TAs engagement:

- The lack of appropriate cooperation between teachers and TAs:

Teachers could misinterpret the role and responsibilities of TAs in a threefold manner. For instance, they could feel threatened by TAs as somebody who is appointed as their (possible) replacement, while their introduction is perceived as the first step in replacing the particular teacher with a new colleague who is perceived as more knowledgeable in teaching Serbian as a non-mother tongue. In addition, teachers could formally accept cooperation with TAs, but diminish the role of TAs by refusing to adapt to the new teaching methods presented by TAs. Furthermore, teachers could wrongly interpret that TAs are now responsible for preparation and realisation of lessons and leave them alone in a class, thus avoiding to fulfil their own duties, yet at the same time being confident that they will bear no negative consequences. Likewise, TAs could also misapprehend their position, by acting like teachers rather than teaching assistants. In order to preclude all misinterpretations of roles and responsibilities, we organised a joint meeting with teachers, TAs and school principals. At the meeting, we once again stressed duties and responsibilities of teachers and TAs. In addition, the monthly report of TAs contains a subsection on cooperation with teachers and on challenges in their work. We agreed that any problem that could arise should be solved in amicable communication among the Project Team, school principals and particular TA and teacher.

In this reporting period we faced the risk in cooperation between the teacher and the teaching assistant where the delegated teacher did not want to cooperate with the assistant. Fortunately, the school management provided full support in order to find a solution for the problem, together with representatives of Group 484 and the Coordination Body for Bujanovac, Preševo and Medveđa. The school management promised to monitor the cooperation between the delegated teacher and the assistant and provide full support, if needed.

Issues that appeared during the implementation of action:

- The work of the Working Group of MESTD for improvement of teaching Serbian as a non-mother tongue

We have been informed by CBO that MESTD will change the mechanism for evaluation and improvement of teaching Serbian as a non-mother tongue. They will not form the Working Group in charge for this issue only, but probably the existing WG of MESTD will become responsible for this matter as well. We are still waiting for official information from MESTD to CBO.

However, we have close cooperation with School Administration of MESTD – Leskovac, responsible for schools in Bujanovac and Preševo and inform them about key project activities. Their representative was present during the testing on 14/15 November.

Forthcoming activities for the period December 2018 to January 2019- Milestone II:

- Conduct regular monitoring and evaluation of TAs’ work and submit relevant documents to the EU PRO to support these activities

- Maintain regular communication with the schools (principals and teachers of SNMT) in the course of the project, ensuring that its implementation goes in accordance with the work plan

- Conduct monthly field visits to the assistants and organise meetings with the TAs and school representatives in order to monitor and evaluate the project progress

Annexes:

- Annex 1. School timetable and number of school students SRB

- Annex 2. TAs Self-evaluation form SRB

- Annex 3. September TAs Monthly reports

- Annex 4. October TAs Monthly reports

Date: 26 November 2018

Signature of responsible person: Robert Kozma, Program Manager

Signature_____________

The Delegation of EU in RS through the program European PROGRES supported efforts of the Ministry of Education, Science and Technological Development and the Coordination Body for Preševo, Bujanovac and Medveđa in implementing recommendations for improvement of teaching of Serbian as a non-mother tongue, while the OSCE Mission to Serbia supported engagement of teaching assistants during the second semester of school year 2017/2018.