Engagement and Monitoring of Assistants to Teachers of Serbian as a Non-Mother Tongue in Selected Elementary Schools in Bujanovac and Preševo

INCEPTION REPORT

(August 2018 to September 2018)

Ref. UNOPS- EUPRO-2018-S-006

September, 2018

Introduction

The Progress Report has been specified as a deliverable in the Contract for Services UNOPS- EUPRO-2018-S-006, related to the consulting services in respect of engagement and monitoring of assistants to teachers of Serbian as a non-mother tongue in 4 elementary schools in Bujanovac and Preševo. The Inception Report was prepared by Robert Kozma, the Project Coordinator, on 27 September.

#### Background

One of the characteristics of Bujanovac and Preševo as post-conflict municipalities is the protracted polarisation of citizens based on their ethnicity and language. This polarisation is also visible in the education system. Schools are not based on ethnic background of students. However, there are separate schools in which teaching is either in Serbian or Albanian. School students of mainly Albanian ethnicity attend schools with tuition in the Albanian language and vice versa, school students of Serbian ethnicity attend schools with tuition in the Serbian language. Children of Roma ethnicity mainly attend the latter schools. Students in the schools where teaching is in Albanian have obligatory subject of Serbian as a non-mother tongue, while there are no courses of the Albanian language as the language of local community offered in schools with teaching in the Serbian language. Inadequate knowledge of the Serbian language among youth of the Albanian national minority seriously damages their opportunities for further education and employment in Serbia, while the lack of bilingualism among all citizens hampers social cohesion in these municipalities. In 2014, the Coordination Body for Preševo, Bujanovac and Medveđa (CBO) conducted research and the following report: the “Study on the Possibilities for Improvement of Teaching/Learning of Serbian as a Non-Mother Tongue in Preševo, Bujanovac and Medveđa”. They have detected that only 5% of Albanian school children from 16 elementary schools encompassed by research have functional ability to communicate in Serbian. One of the main reasons for shortcomings in teaching Serbian as a non-mother tongue is the lack of qualified staff. Because of that, authors of the Study proposed introduction of teaching assistants with appropriate qualifications in teaching methodology of Serbian as a non-mother tongue.  Since 2015, a confluence of stakeholders have supported and implemented recommendations specified in the Study, enabling for six teaching assistants to be engaged in four elementary schools in Preševo and Bujanovac. Project “Engagement and Monitoring of Assistants to Teachers of Serbian as a Non-Mother Tongue in Selected Elementary Schools in Bujanovac and Preševo” builds on the results of previous actions and aims to contribute to the recommendation of the Study and to improvement of social cohesion of Bujanovac and Preševo.

Milestone I – 16 August to 24 September 2018

- Preparatory activities conducted and detailed action plan produced;

- Selection and engagement process of Teaching Assistants (TAs) completed;

- Agreement on defined roles and responsibilities of TAs, teachers and school management reached;

- Engaged experts for Serbian as a non-mother tongue.

Output 1: Preparatory activities conducted

Activity 1.1: Preparatory Activities

At the beginning of the project, the project coordinator and the assistant developed the Action Plan for the project implementation in order to define all activities and responsibilities of the project team and stakeholders throughout the course of the project. For the inception period, the main aim was to conduct a call for application of candidates for the position of teaching assistants and to finish the selection process and engage six teaching assistants, as well as to initiate the first step in conducting baseline testing of school students’ knowledge of the Serbian language i.e. to engage two experts from the Centre for Serbian as a Foreign Language from the Faculty of Philology. (Please see activity 2.1, 3.1, 4.1 and accompanying annexes)

Output 2: Selection and engagement process of Teaching Assistants (TAs) completed

Activity 2.1: Selection of Teaching Assistants

In August, Group 484 established the Selection Commission for realisation of the Call for Applications for six positions of TA in four elementary schools in Bujanovac (“Naim Frašeri” and “Muharem Kadriu”, Veliki Trnovac) and Preševo (“Seljami Halači”, Oraovica, and “Ibrahim Keljmendi”). The members of the Selection Commission were two experts in Serbian as a non-mother tongue from the Centre for Serbian as a Foreign Language from the Faculty of Philology, Vesna Krajišnik, as the Chairman of the Commission and Nikica Strižak, as well as Robert Kozma, the Project Coordinator and Manager of Group 484 Programme for Intercultural Dialogue. Additionally, Katarina Najdanović, Project Associate at the Coordination Body’s Office of the Government of the Republic of Serbia for the municipalities of Preševo, Bujanovac and Medveđa, and Biljana Kerić, Programme Associate for Social Cohesion at EU PRO UNOPS had the observer status in the Selection Commission.

The Call for Application for the selection of six Teaching Assistants of Serbian as a non-mother tongue was launched on 24 August 2018 and was opened until 2 September 2018. It was publicised at the website and Facebook page of Group 484 and at the EU PRO’s Facebook page. The Application consisted of an application form, motivation letter and proof of graduation (a degree in teaching the Serbian language and literature). The candidates needed to fulfil the following qualifications: Serbian citizenship and the university degree in teaching the Serbian language and literature, as well as communication and presentation skills, basic IT knowledge and writing and reporting skills. Experience in teaching Serbian as a non-mother tongue or Serbian as a foreign language was considered an advantage, as well as any experience in working in Bujanovac or Preševo, basic knowledge of the Albanian language and completed training or seminars on intercultural education. Additionally, the Selection Commission valued candidates’ openness, sensibility and readiness for living and working in multicultural environment.

We received 18 applications, of which three candidates failed to fulfil the qualification requirements. They did not have the university degree in teaching the Serbian language and literature, thus, they were not considered for the next phase of the selection process. After the first screening of the applications, the Selection Commission selected four candidates who had been engaged as teaching assistants of Serbian as a non-mother tongue in the previous iterations of the project, taking into account good results they had achieved through their previous engagement. Those four candidates are: Dragana Milutinović, Marko Radulović, Brankica Živković and Ivana Milenković.

The Selection Commission selected 11 candidates that had fulfilled necessary criteria stipulated in the Call for Applications and invited them for an interview. Interviews were held in Vranje on 7 September at the premises of UNOPS – Office in Vranje and in Belgrade on 10 September at the premises of Group 484. During the interviews in Vranje, Bejtula Mustafa, official of the Coordination Body’s Office of the Government of the Republic of Serbia for the municipalities of Preševo, Bujanovac and Medveđa was present to assess the candidates’ knowledge of the Albanian language. At the interviews, the Selection Commission assessed and valued motivation of candidates for working as TAs, their openness and readiness to work in multicultural environment and their competence and expertise to teach Serbian as a non-mother tongue. Upon the interviews, the Commission selected two best candidates:  Marija Kostadinović and Vlada Petrović. Additional two candidates were selected to be on a waiting list, in case some of the selected candidates declined the job offer. However, all six selected candidates accepted job offers and signed contracts.

Activity 2.2. Engagement of Teaching Assistants

After the contract signing, engagement of the assistants started on 17 September 2018. Each assistant is engaged for the period of 10 months. They are assigned to the appropriate teachers of Serbian as a non-mother tongue and will have full class load (18 school classes per week). They will teach in the fourth and sixth grades of the selected schools. This will be a continuation of the work from the previous year, where the assistants worked with the third and fourth grade school students. During the meeting organised on 13 September 2018 in Presevo and Bujanovac, we agreed that the assistants needed to have a full class load. The expert suggested that if teaching assistants did not have a full class load, they should take lower grades, where the school students did not have the opportunity to learn Serbian with teaching assistants. This was negotiated with the school principals and teachers. We agreed upon the full class load according to the school timetable (please see Activity 3.2.).

The Teaching Assistants’ main role is to help teachers of Serbian as a non-mother tongue employed in the schools to improve their teaching skills, modernise their approach in teaching this school subject and introduce novelties in teaching by organising interactive workshops, games and quizzes in order to enhance the students' fluency in Serbian. Besides teaching, the assistants have an obligation to prepare and submit monthly reports, where they will summarise their activities. We have offered all support to the assistants and we are in constant communication with them. So far, close communication with assistants has been focused on school timetables, monthly reporting, etc. All teaching assistants participated in training on learning outcomes of the new curricula for Serbian as a non-mother tongue for the first and the second cycle of education, on 15-16 September in Bujanovac and Preševo which was organized by the MESTD, the Institute for the Advancement of Education and OSCE – Mission in Serbia. One of the trainers was Nikica Strižak, the expert included in our project. She used this opportunity to mentor and advice teaching assistants, especially two new ones, on teaching methods in order to prepare them for assisting in teaching.

It was agreed that Gordana Đurašević, Project Assistant, will be in communication with TAs, providing them support when needed. TAs will be obliged to submit written reports about their work in schools on the twentieth of the month.

Output 3: Agreement on defined roles and responsibilities of TAs, teachers and school management reached

Activity 3.1: Informing the schools on the start of the project

On 10 September, the Ministry of Education, Science and Technological Development sent a letter of agreement to CBO regarding the project continuation and engagement of teaching assistants in respective schools in Bujanovac and Preševo. CBO immediately informed respective schools on the project continuation and invited them to a meeting to define roles and responsibilities of TAs and teachers (please see Activity 3.2.). CBO informed and invited School Administration of MESTD – Leskovac to the forthcoming meeting.

Activity 3.2: Meeting with school directors, teachers and TAs

On 13 September 2018, the project team and Nikica Strižek held meetings with school management representatives, teachers and the TAs in Preševo and Bujanovac. Representative of School Administration of MESTD – Leskovac, Behljuj Nasufi, participated in the meeting held in Preševo. He informed the project team and school managements that he will conduct monitoring visits in the schools in order to assess the cooperation of TAs and teachers.

The aim of the meetings was to reach agreement on a full class load of TAs, consisting of 18 working hours within school classes, as well as on grades in which TAs will assist in teaching and cooperate with. We also spoke about the roles and responsibilities of TAs, teachers and school principals, as well as about the desired principles for cooperation between teachers and TAs. The first working day of TAs was set to be 17 September.

Meeting in Preševo: It was held at the premises of the CB’s Office in Preševo. We agreed that TAs would be engaged in the schools in following way:

- Dragana Milutinović will continue to work in “Seljami Halači” Elementary School in Oraovica, Preševo, in all classes of IV and VI grades. She will continue supporting the same school students in learning the Serbian language as she did last year. She will have additional six school classes assisting in teaching in two classes of V grade.

- Ivana Milenković will continue to work in “Ibrahim Keljmendi” Elementary School by assisting teachers in six classes of VI grades. In this way, she will be supporting the same students as she did last year.

- Marija Kostadinović, will start working in “Ibrahim Keljmendi” Elementary School and assisting in teaching to all classes of IV grade and in one class of VI grade.

To conclude, all 16 classes of IV and VI grades of these two elementary schools will be covered by TAs, as well as additional two classes of V grade in “Seljami Halači” Elementary School. In total, 4 teachers and estimated 387 children will be supported by the assistants.

Meeting in Bujanovac: It was held at the premises of the CB’s Office in Bujanovac. The following was agreed:

- Brankica Živković will continue to work in “Naim Frašeri”” Elementary School, assisting in teaching in all classes of IV and VI grades. In this way, she will be supporting the same students as she did last year. She will also have additional six school classes by covering two classes of III grade.

- Marko Radulović and Vlada Petrović will work in “Muharem Kadriu” Elementary School, Veliki Trnovac. Marko Radulović will assist in teaching in four classes of IV grade. (Please note that one class consists of students from both III and IV grades.) He will also have additional six school classes by covering two classes of III grade.

- Vlada Petrović will assist in teaching in three classes of VI grade and will have additional 10 school classes in four classes of V and VIII grades.

To conclude, all four classes of IV and VI grades of “Naim Frašeri” Elementary School and four classes of IV grade and all three classes of VI grade of “Muharem Kadriu” Elementary School will be covered by TAs. (Please note that one class of IV grade, i.e. IV-4 class, is not covered by TA.) Additional eight classes of III, V, VII and VIII grades in these two schools will be covered by TAs. In total, 5 teachers and estimated 365 children will be supported by the assistants.

Note: All TAs have a class load of 18 school classes per week, while only Vlada Petrović has a class load of 19 school classes. All classes of IV and VI grades are covered in all 4 schools, except in “Muharem Kadriu” Elementary School. Currently, one class of IV grade is not covered because the school lessons of Serbian as a non-mother tongue are being constantly overlapped with other lessons. We are in communication with the school principal in order to reach agreement on rescheduling lessons, but it could be challenging since the school have two separate premises in which the educational process is being organised.

Output 4: Experts for Serbian as a non-mother tongue engaged

Activity 4.1: Meeting with the experts

At the beginning of project, the project coordinator held a meeting with Nikica Strižak and Vesna Krajišnik from the Centre for Serbian as a Foreign Language from the Faculty of Philology of the University of Belgrade. The following was agreed:

- Two experts would participate in the selection process of six teaching assistants of Serbian as a non-mother tongue, as members of the Selection Commission. Their duty would be to assess expertise, knowledge and experience of candidates in teaching Serbian as a non-mother tongue.

- They will design one model exam for assessing school students’ knowledge of the Serbian language for each planned class and grade (i.e. baseline testing); design detailed instructions for teachers and teaching assistants for implementation of the model exam; participate in conducting the model exam in the school year 2018/2019 in all four elementary schools in Bujanovac and Preševo encompassed by the project; write the assessment report on achieved testing results and recommend further steps for improvement of the teaching process of Serbian as a non-mother tongue.

- They would participate in meetings of the Working Group of the Ministry of Education, Science and Technological Development (MESTD) for improvement of teaching of Serbian as a non-mother tongue, if the Group was established by the MESTD.

The experts accepted terms and conditions of their engagement and signed contracts on 31 August, which was followed by their participation in the Selection Commission, interviews with candidates that were selected for the second round of the selection process, evaluation of the candidates’ knowledge of Serbian as a non-mother tongue and understanding of teaching methods, as well as providing insights and suggestions to TAs on the curricula and teaching methods in order to initiate learning process among school students and properly cooperate with appointed teachers.

Activity 4.2: Realisation of baseline testing of school students’ knowledge of Serbian as a non-mother tongue

Although the project timeframe stipulates that baseline testing should be conducted in November 2018, the experts for Serbian as a non-mother tongue proposed to delay the realisation of testing for February 2019. The reason for that is that the last testing within the action was conducted in May 2018. Moreover, on 21 September, the Institute for the Advancement of Education with the support of the OSCE – Mission in Serbia conducted testing of knowledge of the Serbian language for 1st and 5th grade students of elementary schools in Bujanovac and Preševo. A new testing in October probably would be too much for school students, teachers and school management. Furthermore, teaching assistants entered classes on 17 September and thus there would insufficient time for the improvement of teaching process if testing was conducted in October. There is a possibility that improvement of students’ knowledge could not be detected compared with the results from May. Then again, the EU PRO representative suggested baseline testing to be conducted only with school students from the grades newly included in the project. Their knowledge will then be the starting point for future comparison and evaluation of engagement of teaching assistants. We have agreed to decide on this issue until the end of the first week of October upon the joint consultations of representatives of the EU PRO, CBO, Group 484 and the experts. The MESTD will also be consulted.

Risk and issues:

Possible risks in implementation of action are related to communication and cooperation with schools and TAs engagement:

- The lack of appropriate cooperation with school management:

School principals could be reluctant to cooperate with the project team in implementation of activities, especially in designing schedule of school classes in order to ease the work of teaching assistants and to include them in assisting in teaching to pupils of IV and VI grades. If such issue arises, we will organise a meeting with school management in order to find appropriate solution and kindly remind them that this process is supported by the MESTD.

- The lack of appropriate cooperation between teachers and TAs:

Teachers could misinterpret the role and responsibilities of TAs in a threefold manner. For instance, they could feel threatened by TAs as somebody who is appointed as their (possible) replacement, while their introduction is perceived as the first step in replacing the particular teacher with a new colleague who is perceived as more knowledgeable in teaching Serbian as a non-mother tongue. In addition, teachers could formally accept cooperation with TAs, but diminish the role of TAs by refusing to adapt to the new teaching methods presented by TAs. Furthermore, teachers could wrongly interpret that TAs are now responsible for preparation and realisation of lessons and leave them alone in a class, thus avoiding to fulfil their own duties, yet at the same time being confident that they will bear no negative consequences. Likewise, TAs could also misapprehend their position, by acting like teachers rather than teaching assistants. In order to preclude all misinterpretation of roles and responsibilities, we organised a joint meeting with teachers, TAs and school principals. At the meeting, we once again stressed duties and responsibilities of teachers and TAs. In addition, the monthly report of TAs contains a subsection on cooperation with teachers and on challenges in their work. We agreed that any problem that could arise should be solved in amicable communication between project team, school principals and particular TA and teacher.

- Two newly appointed TAs did not go through training on teaching methods before entering classes.

The MESTD, the Institute for the Advancement of Education and OSCE – Mission in Serbia organised training on learning outcomes of the new curricula for Serbian as a non-mother tongue for the first and the second cycle of education, on 15-16 September in Bujanovac and Preševo. One of the trainers was Nikica Strižak, the expert included in our project. She used this opportunity to mentor and advice teaching assistants.

Issues that appeared during the implementation of action:

- Timeframe for conducting baseline testing of school students.

Please see Activity 4.2.

- The work of the Working Group of MESTD for improvement of teaching Serbian as a non-mother tongue

We have been informed by CBO that MESTD will change a mechanism for evaluation and improvement of teaching Serbian as a non-mother tongue. They will not form the Working Group in charge only for this issue, but probably an already existing WG of MESTD will become responsible for this matter as well. We are waiting for official information from MESTD to CBO. If no stakeholder involved in the project becomes a member of such a WG, we will initiate close cooperation with School Administration of MESTD – Leskovac, responsible for schools in Bujanovac and Preševo.

Forthcoming activities for the period October to November - Milestone II:

- Conduct regular monitoring and evaluation of TAs’ work and submit relevant documents to the EU PRO to support these activities

- Maintain regular communication with the schools (principals and teachers of SNMT) in the course of the project, ensuring that its implementation goes in accordance with the work plan

- Conduct monthly field visits to the assistants and organise meetings with the TAs and school representatives in order to monitor and evaluate the project progress

- Preparation and realisation of baseline testing of school students’ knowledge by experts

Annexes:

- Annex 1. Action Plan and Timeline of Project_ENG

- Annex 2. Call for Applications for Engagement of TAs_SRB

- Annex 3. Evaluation Report for Engagement of TAs SRB

- Annex 4. Decision on Selection and Engagement of 6 TAs SRB

- Annex 5. Contracts with TAs SRB

- Annex 6. TAs Monthly Report form SRB

- Annex 7. Contracts with Experts for the Serbian Language as a Non-mother Tongue SRB

- Annex 8. Contact Sheet

Date: 27 September 2018

Signature of responsible person: Robert Kozma, Program Manager

signature_____________

The Delegation of EU in RS through the program European PROGRES supported efforts of the Ministry of Education, Science and Technological Development and the Coordination Body for Preševo, Bujanovac and Medveđa in implementing recommendations for improvement of teaching of Serbian as a non-mother tongue, while the OSCE Mission to Serbia supported engagement of teaching assistants during the second semester of school year 2017/2018.

Annex 1_Action Plan and Timeline of Project_ENG

Annex 2_Call for applications for engagement of TAs_SRB

http://grupa484.org.rs/konkurs_asistenti_u_nastavi/

Annex 5. Contracts with TAs SRB

Annex 6. TAs Monthly report form SRB

Annex 7. Contracts with experts for the Serbian language as a non-mother tongue SRB